## Sheet2
Uniq No | Nd Nim No | ID Tiara Enom | Order Batch | Witel | Site ID | Jumlah NE | SITE NAME | Main Program | Detail Program | BW Order | Start Target Date | Target Date | Status Final (OPEN /CLOSED) | KET | Ba No | Tgl Ba(Date) | Created At (Date) | Updated At (Date)
324 | 1701/TC.01/VS-01/XI/2023 | 484346 | 2023 | SOLO | SLO812 | 1 | Edutorium UMS | FIRO | Permohonan Kebutuhan New Link Telkom Support Program Permanenisasi Batch#1 Regional Jawa Tengah 2023 | 950 | 2023-11-22 | 2024-02-20 | Open | Assessment DID
325 | 1701/TC.01/VS-01/XI/2023 | 484344 | 2023 | SOLO | SLO832 | 1 | Stadion Manahan | FIRO | Permohonan Kebutuhan New Link Telkom Support Program Permanenisasi Batch#1 Regional Jawa Tengah 2023 | 950 | 2023-11-22 | 2024-02-20 | Open | Assessment DID
326 | 1701/TC.01/VS-01/XI/2023 | 484342 | 2023 | SOLO | SKH022 | 1 | Blue Sukoharjo 01 | FIRO | Permohonan Kebutuhan New Link Telkom Support Program Permanenisasi Batch#1 Regional Jawa Tengah 2023 | 950 | 2023-11-22 | 2024-02-20 | Open | Assessment DID
327 | 1701/TC.01/VS-01/XI/2023 | 484340 | 2023 | SOLO | SKH146 | 1 | Bakalan Polokarto | FIRO | Permohonan Kebutuhan New Link Telkom Support Program Permanenisasi Batch#1 Regional Jawa Tengah 2023 | 950 | 2023-11-22 | 2024-02-20 | Open | Assessment DID
328 | 1112/TC.01/VS-01/II/2023 | 460504 | 2023 | MAGELANG | MKD672 | 1 | PASURUHANTBG | FIMO | Permohonan Kebutuhan Upgrade Endsite & New Link (FIMO) Support Program Capacity Transport Access 2023 Batch#2 Regional Jawa Tengah | 950 | 2023-02-21 | 2023-05-22 | Open | Procurement Process
329 | 1112/TC.01/VS-01/II/2023 | 460503 | 2023 | MAGELANG | MKD673 | 1 | RINGINANOMTBG | FIMO | Permohonan Kebutuhan Upgrade Endsite & New Link (FIMO) Support Program Capacity Transport Access 2023 Batch#2 Regional Jawa Tengah | 950 | 2023-02-21 | 2023-05-22 | Open | Procurement Process
330 | 1918/TC.01/KP-01/XII/2022 | 400750 | 2022 | MAGELANG | WNO691 | 4 | LANCAR-3307010010 | FIRO | Permohonan Transport Upgrade dan FIMO Support Program Settlement Batch 6 Jawa Tengah | 95 | 2022-12-23 | 2023-03-23 | Open | Waiting Allocation Budget
331 | 1918/TC.01/KP-01/XII/2022 | 400752 | 2022 | SOLO | WNG058 | 10 | MIJILDMT | FIRO | Permohonan Transport Upgrade dan FIMO Support Program Settlement Batch 6 Jawa Tengah | 285 | 2022-12-23 | 2023-03-23 | Open | Waiting Allocation Budget
332 | 1918/TC.01/KP-01/XII/2022 | 397666 | 2022 | SOLO | SKH102 | 9 | MANANGDMT | FIRO | Permohonan Transport Upgrade dan FIMO Support Program Settlement Batch 6 Jawa Tengah | 140 | 2022-12-23 | 2023-03-23 | Open | L0 - Progress FO
333 | 1918/TC.01/KP-01/XII/2022 | 398455 | 2022 | KUDUS | PAT702 | 7 | BLUEJOLONGPATI | FIRO | Permohonan Transport Upgrade dan FIMO Support Program Settlement Batch 6 Jawa Tengah | 110 | 2022-12-23 | 2023-03-23 | Open | L2 - Ready
334 | 1918/TC.01/KP-01/XII/2022 | 400753 | 2022 | KUDUS | PAT050 | 7 | Beketel Kayen | FIRO | Permohonan Transport Upgrade dan FIMO Support Program Settlement Batch 6 Jawa Tengah | 144 | 2022-12-23 | 2023-03-23 | Open | Waiting Allocation Budget
335 | 1918/TC.01/KP-01/XII/2022 | 400716 | 2022 | SEMARANG | KND033 | 9 | Sidokumpul ex Botomulyo | FIRO | Permohonan Transport Upgrade dan FIMO Support Program Settlement Batch 6 Jawa Tengah | 110 | 2022-12-23 | 2023-03-23 | Open | Waiting Allocation Budget
336 | 1918/TC.01/KP-01/XII/2022 | 398462 | 2022 | PURWOKERTO | CLP791 | 4 | BLUETAMBAKREJA | FIRO | Permohonan Transport Upgrade dan FIMO Support Program Settlement Batch 6 Jawa Tengah | 190 | 2022-12-23 | 2023-03-23 | Open | Waiting Allocation Budget
337 | 1918/TC.01/KP-01/XII/2022 | 398447 | 2022 | PURWOKERTO | CLP755 | 3 | CIJATI | FIRO | Permohonan Transport Upgrade dan FIMO Support Program Settlement Batch 6 Jawa Tengah | 110 | 2022-12-23 | 2023-03-23 | Open | Waiting Allocation Budget
338 | 1918/TC.01/KP-01/XII/2022 | 398448 | 2022 | KUDUS | BLA009 | 7 | KARANGJONGDMT | FIRO | Permohonan Transport Upgrade dan FIMO Support Program Settlement Batch 6 Jawa Tengah | 110 | 2022-12-23 | 2023-03-23 | Open | Waiting Allocation Budget
339 | 1171/TC.01/KP-01/III/2022 | 208424 | 2022 | MAGELANG | KBM048 | 8 | ARGOPENI | FIRO | Permohonan Transport Settlement#11-Outstanding Jawa Tengah Part 3 | 220 | 2022-03-28 | 2022-06-26 | Open | Waiting Allocation Budget